{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":29,"n_cols":6,"rows_kept":29,"cut":false,"hidden":false,"merged":[[19,0,24,0],[1,0,1,5],[25,5,28,5],[19,5,24,5],[25,0,28,0],[7,0,10,0],[12,0,18,0],[4,0,6,0]]}
[]
["미완료내역"]
[]
["구분","항목","완료예정일","개발진행사항","테스트가능일","사전준비작업 및 이슈"]
["어드민","쿠폰관리 기능","2021-05-21","AZURE에서 발생되는 오류건 수정 완료","2021-05-24"]
[null,"정산","2021-06-18","화면은 완료하였음. 데이터 조회 및 정산확정 처리 기능만 구현하면 됨. 5/31일부터 개발 시작","2021-06-21","1. 화면별 개발이 완료되면 화면별로 확인 요청할 예정\n2. 데이터 검증은 ~6/30일까지 진행"]
[null,"통계","2021-06-18","6/1일부터 개발 시작","2021-06-21","1. 화면별 개발이 완료되면 화면별로 확인 요청할 예정\n2. 데이터 검증은 ~6/30일까지 진행"]
["SCM","쿠폰관리 기능","2021-05-23","완료","2021-05-24"]
[null,"주문관련 기능","2021-05-21","완료","2021-05-24"]
[null,"이미지대량등록 기능","2021-05-19","완료","2021-05-24"]
[null,"딜상품관리","2021-05-28",null,"2021-06-01"]
["프론트","상품리스트 -> 상품상세 이동 -> 히스토리백 기능","2021-06-04",null,"2021-06-07","스크롤이 최상단에서 해당 위치로 스크롤링 되며 이동하는 현상이 재현되고 있음"]
["3rd party\n연동","검색엔진 연동 (프론트)","2021-05-28",null,"2021-06-01","1. 화면 데이터 노출을 5/28일까지 완료\n2. 데이터 검증 및 성능 이슈에 따른 보완은 ~6/30일까지 진행"]
[null,"넷퍼시 메일 발송 연동","2021-06-04","1. 공통 모듈 개발 완료\n2. 자동메일의 업무단 적용은 6/4일한 완료 예정","2021-06-07","메일발송 shooter가 신규DB로의 연계가 불가하여, 특정일자를 선정하여 테스트 진행하려고 함"]
[null,"알림톡/SMS/LMS 발송 연동","2021-06-04","1. 알림톡 템플릿 신세계아이앤씨 업체에 전달 완료\n2. 공통 모듈 개발 완료\n3. 업무단 적용은 6/4일한 완료 예정","2021-06-07"]
[null,"샵링커API를 통한 제휴몰 연동","2021-06-04","1. 상품등록 연동 완료\n2. 주문수집 개발중","2021-06-07","XML이 생성될 서버 경로 설정. 외부에서 호출이 가능해야 함"]
[null,"추천솔루션 연동 (프론트)","미정",null,null,"업체에 6/1 ~ 6/4일간 1차 개발 미팅 요청"]
[null,"EP(네이버, 다음)","2021-06-11",null,"2021-06-14","1. 파일이 생성될 서버 경로 설정. 외부에서 호출이 가능해야 함\n2. 생성된 파일을 패션개발팀에 전달 및 검증 요청"]
[null,"광고스크립트 적용","2021-06-18",null,"2021-06-21","광고스크립트 업체에 검증 요청"]
["마이그레이션","회원정보(암호화, 탈퇴, 휴면 처리)","2021-05-27",null,null,"협의 필요 사항\n1. 오픈 일주일 전 상품 프리징\n2. 주문 5년치 중 4년치는 오픈 2일전 마이그레이션 수행\n3. 회원정보 암호화는 3일전 수행하고 오픈일에 신규/탈퇴/휴면회원에 대해서만 업데이트"]
[null,"회원환불계좌","2021-05-27","평문 데이터 제공받지 못함 (패션개발팀에 요청)"]
[null,"주문수량부분취소","2021-05-30"]
[null,"교환/반품","2021-05-30"]
[null,"구매확정","2021-05-30"]
[null,"품목 재정비에 따른 작업","2021-05-27"]
["앱","동영상 업로드","2021-05-23","AOS, IOS 개발 완료","2021-05-24","1. 앱이 현재 http://ts5000.ipdisk.co.kr/ 로 연결되어 apk 파일을 배포하여 이 도메인에서만 테스트 가능\n2. IOS 테스트를 위한 testflight 설정을 위한 계정 전달"]
[null,"스플래쉬 이미지 처리","2021-05-25","AOS, IOS 개발 완료","2021-05-26"]
[null,"푸시알림 목록 리스트","2021-05-26",null,"2021-05-27"]
[null,"선물하기의 연락처 정보","2021-05-30",null,"2021-06-01"]